## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
Sprint 1 | Sprint 1 | US-1 | Setup Project Environment (JDK, IntelliJ, GitHub) — Configure development tools, initialize Git repository | MUST HAVE | None | Sujan Poojary | 3- Completed
Sprint 1 | Sprint 1 | US-2 | Implement Product Model & InventoryManager using OOP — Design core classes with attributes and methods following OOP principles | MUST HAVE | US-1 | Sujan Poojary | 3- Completed
Sprint 1 | Sprint 1 | US-3 | Add Exception Handling for Inventory Operations — Integrate try-catch blocks and meaningful error messages for smooth program execution. | MUST HAVE | US-2 | Sujan Poojary | 3- Completed
Sprint 1 | Sprint 1 | US-4 | Implement Persistence with CSV & Git Workflow — Enable data saving/loading from CSV files and maintain version control with Git. | MUST HAVE | US-3 | Sujan Poojary | 3- Completed
Sprint 1 | Sprint 1 | US-5 | Database Basics: SQL Practice + JDBC Test Connection — Practice SQL CRUD operations and verify Java-to-DB connectivity. | MUST HAVE | US-4 | Sujan Poojary | 3- Completed
Sprint 1 | Sprint 1 | US-6 | Documentation & Setup Verification | SHOULD HAVE | None | Sujan Poojary | 3- Completed
Sprint 2 | Sprint 2 | US-7 | Implement Read Operations (getAll, getById) — Enable listing all items and fetching specific products via console menu. | MUST HAVE | US-5 | Sujan Poojary | 3- Completed
Sprint 2 | Sprint 2 | US-8 | Implement Update & Delete Operations — Add functionality to modify and remove products from the inventory. | MUST HAVE | US-7 | Sujan Poojary | 3- Completed
Sprint 2 | Sprint 2 | US-9 | Integrate CRUD into Console Menu (End-to-End Test) — Merge all CRUD options into a single menu interface for user interaction. | MUST HAVE | US-8 | Sujan Poojary | 3- Completed
Sprint 2 | Sprint 2 | US-10 | Implement CSVHelper for exporting inventory data | MUST HAVE | US-9 | Sujan Poojary | 3- Completed
Sprint 2 | Sprint 2 | US-11 | Add Input Validation & Error Handling — Prevent invalid data entries and improve user input reliability. | MUST HAVE | US-9 | Sujan Poojary | 3- Completed
Sprint 2 | Sprint 2 | US-12 | JUnit Testing for Core Modules — Write and execute unit tests to verify CRUD and validation functionalities. | MUST HAVE | US-11 | Sujan Poojary | 3- Completed
Sprint 2 | Sprint 2 | US-13 | Sprint Review — Clean redundant code, improve structure, and prepare for next sprint integration. | SHOULD HAVE | None | Sujan Poojary | 3- Completed
Sprint 3 | Sprint 3 | US-14 | Implement CSVHelper for Exporting Inventory Data | MUST HAVE | US-10 | Sujan Poojary | 3- Completed
Sprint 3 | Sprint 3 | US-15 | Implement EmailService for Report Delivery (SMTP) Configure JavaMail API to send CSV reports | MUST HAVE | US-14 | Sujan Poojary | 3- Completed
Sprint 3 | Sprint 3 | US-16 | Add “Generate Report” Option in Admin Menu — Provide admin interface to trigger inventory report generation. | SHOULD HAVE | US-15 | Sujan Poojary | 3- Completed
Sprint 3 | Sprint 3 | US-17 | Integrate DB + CSV + Email Modules for Full Reporting — Combine data export and email sending for automated report workflow | MUST HAVE | US-16 | Sujan Poojary | 3- Completed
Sprint 3 | Sprint 3 | US-18 | Implement OTP-Based User Verification — Generate and validate OTP during registration for secure account setup. | SHOULD HAVE | US-17 | Sujan Poojary | 3- Completed
Sprint 3 | Sprint 3 | US-19 | Add “Verify Email” & “Resend OTP” Options — Add verification retry options for smoother user registration flow. | COULD HAVE | US-18 | Sujan Poojary | 3- Completed
Sprint 4 | Sprint 4 | US-20 | Implement Stock Monitoring Logic — Develop backend logic to identify and flag low-stock items automatically. | MUST HAVE | US-19 | Sujan Poojary | 3- Completed
Sprint 4 | Sprint 4 | US-21 | Develop Automated Stock Alert Generator — Schedule background job to email alerts for low inventory | MUST HAVE | US-20 | Sujan Poojary | 3- Completed
Sprint 4 | Sprint 4 | US-22 | Integrate Email Notifications for Low-Stock Products — Combine alert logic with EmailService for full automation. | MUST HAVE | US-21 | Sujan Poojary | 3- Completed
Sprint 4 | Sprint 4 | US-23 | Implement System-Wide Error Logging & Debug Mode — Log exceptions and add debug configuration for easier maintenance | SHOULD HAVE | US-22 | Sujan Poojary | 3- Completed
Sprint 4 | Sprint 4 | US-24 | Enhance UI for Admin Console — Improve menu design with better formatting and colored outputs for readability. | COULD HAVE | None | Sujan Poojary | 3- Completed
Sprint 4 | Sprint 4 | US-25 | Package & Deploy Full Inventory Management System — Final testing, documentation, and project deployment. | MUST HAVE | US-24 | Sujan Poojary | 3- Completed
Note on F1: ====== ID#AAABqnR-1bo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Mention the US ID(s) on which the user story depends.